## Phases and Tasks
Phase | Task Description | Timeline
Phase 1: Requirement Analysis and Planning | • Gather project requirements through user surveys and interviews. • Analyze existing platforms for benchmarking. • Identify critical features like search filters, recommendation algorithms, and user management systems. | Month 1-2
Phase 2: System Design and Development | • Develop the front-end using responsive web technologies. • Implement back-end processes with Spring Boot. • Design the recommendation engine with ML algorithms (e.g., Rule-based algorithms). • Configure the MySQL database for data storage. | Month 3-6
Phase 3: Testing and Integration | • Conduct functional, integration, and performance testing. • Test for scalability on the Cloud Platform. • Ensure seamless interaction between all components. | Month 7-8
Phase 4: Deployment and Maintenance | • Deploy the platform on a live server. • Monitor system performance. • Address bugs and update the system based on early feedback. | Month 9
Phase 5: Feedback and Iteration | • Collect and analyze user feedback. • Refine features and optimize functionality. • Incorporate new features for an improved user experience. | Month 10

## Gantt Chart
Month/Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Phase 1: Requirement Analysis and Planning
Phase 2: System Design and Database development
Phase 3: Backend API Development
Phase 4: Frontend Development
Phase 5: Testing and Integration
Phase 6: Deployment and Maintenance
Phase 7: Feedback and Iteration